## Project_Daily_Status
Virtual Classroom Project (StudyGeek)
DATE | DAY | Activities | Completion Status (%) | Remarks
2020-06-17 | Wednesday | Project Discussion and Gathering Ideas | 100% | Completed
2020-06-18 | Thrusday | Discussing Features and Preparing SRS | 100% | Completed
2020-06-19 | Friday | Discussing Features and Preparing SRS | 15% | Completed
2020-06-20 | Saturday | Preparing SRS & Database Design | 100% | Completed
2020-06-21 | Sunday | Finalizing SRS & Discussing UI Design | 100% | Completed
2020-06-22 | Friday | Working on UI Pages (Frontend) | 75% | Temporary Design is ready
2020-06-23 | Tuesday | Working on Backend (Modules and Analysis) | 90% | Mostly Completed
2020-06-24 | Wednesday | Working On Different Pages | 40% | Completed
2020-06-25 | Thursday | Working On Different Pages | 70% | in progress
2020-06-26 | Friday | Enhancing UI of designed pages | 100% | Completed
2020-06-27 | Saturday | Backend processes | 80% | in progress
2020-06-28 | Sunday | Working on assigmnets, feedback, query form,profile | 40% | in progress

## Project_TimeLine
SNO | Milestone | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Remarks
1 | SRS | 2020-06-17 | 2020-06-19 | 2020-06-19 | 2020-06-21 | 100% completed, on standby for review.
2 | Project Report | 2020-06-21 | 2020-06-23 | 2020-06-21 | 2020-06-23
3 | Login Page | 2020-06-21 | 2020-06-21 | 2020-06-21 | 2020-06-21 | 100% completed
4 | Designing Dashboard | 2020-06-23 | 2020-06-27 | 2020-06-23 | 2020-06-27 | 100% completed
5 | Query forum | 2020-06-24 | 2020-06-24 | 2020-06-24 | 2020-06-24 | In Progress (Late)
6 | Assignments | 2020-06-26 | 2020-06-27 | 2020-06-26 | 2020-06-27 | In Progress (Late)
7 | Feedback Portal | 2020-06-24 | 2020-06-24 | 2020-06-24 | 2020-06-28 | 100% completed
8 | Sessions | 2020-06-23 | 2020-06-25 | 2020-06-23 | 2020-06-28 | 100% completed
9 | Logo designing | 2020-06-23 | 2020-06-23 | 2020-06-23 | 2020-06-23 | 100% completed
10 | Calender | 2020-06-26 | 2020-06-27 | 2020-06-26 | 2020-06-27 | simple calender ready
11 | Adding modules | 2020-06-24 | 2020-06-24 | 2020-06-24 | 2020-06-24 | 90% completed. UI enhance to be done.
12 | Email Portal | 2020-06-26 | 2020-06-28 | 2020-06-26 | 2020-06-28 | 100% completed
13 | Though of the day | 2020-06-26 | 2020-06-28 | 2020-06-26 | 2020-06-28 | 100% completed
14 | Profile Page | 2020-06-28 | 2020-06-28 | 2020-06-28 | 2020-06-28 | In Progress
15 | Contacts Page | 2020-06-25 | 2020-06-25 | 2020-06-26 | 2020-06-26 | 100% completed
16 | Collating all the finalized pages in the dashboard | 2020-06-24 | 2020-06-24 | 2020-06-28 | 2020-06-28 | Compiled the pages that are complete. Incompleted pages to be compiled later
90% completed. final testing comments to be included later