## Sheet1
myLearnzia (LMS)
DATE | DAY | Shivani Srivastava | Sanjukta | Dia | Kush | Rishabh | Remarks
2020-06-17 | Wednesday | Project Discussion | Project Discussion | Project Discussion | Project Discussion | Project Discussion and Gathering Ideas | Project Discussion and Gathering Ideas
|  | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress
2020-06-18 | Thrusday | Project Discussion and adding features. | Project Discussion and adding features. | Project Discussion and adding features. | Project Discussion and adding features. | Project Discussion and adding features. | Preparing SRS and Discussing Features
|  | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress
2020-06-19 | Friday | Gathering resources | Gathering resources | Gathering resources | Gathering resources | Gathering resources | Gathering resources
|  | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress
2020-06-20 | Saturday | Deciding database tables | Deciding database tables | Preparing SRS | Deciding database tables | Deciding database tables | Preparing SRS & Database Design
|  | Database design Ready | Database design Ready | SRS overview is ready | Database design Ready | Database design Ready | Database Design and SRS design ready
2020-06-21 | Sunday | Query Page UI and Algorithm and LOGO designing | Feedback page UI and Algorithm | Compilation of the Project Report | Login page Backend | Working on Technical Details (SDLC Layers) in SRS | Started on the coding part.
|  | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | SRS completed
2020-06-22 | Monday | Query Page UI and Algorithm | Feedback page UI and Algorithm | Finalizing Project Report | Dashbaord Designing | Working on Technical Details (SDLC Layers) in SRS | Project Report completed.
|  | In-Progress | In-Progress | Completed | Done | Done | Done
2020-06-23 | Tuesday | LOGO finalization | Feedaback Ul and Algorithms | LOGO Designing | Finalizing Dashboard Modules | Preparing for exam | Logo Complete.
|  | Done | In-Progress | Done | Done |  | Logo Design completed.
2020-06-24 | Wednesday | Query Page UI and Algorithm | Assignment UI and algorithms | Started login page algorithms | I contacts Front end | Session UI and Algorithm | I contacts Completed
|  | In-Progress | In-Progress | In-Progress | Done | In-Progress | Session and assignments In-Progress
2020-06-25 | Thrusday | Calendar UI and algorithm | Assignment UI and algorithm | Login Page Designing | Modules Hardcoding | Session UI and Algorithm | Session page ready
|  | Done | In-Progress | Done | In-Progress | In-Progress | Done
2020-06-26 | Friday | Query Page UI and Algorithm | Assignment UI and algorithm | Email and thought of thay Front end and back end | Passcode Validation | Notes Panel | Calender is finalized
|  | In-Progress | In-Progress | In-Progress | In-Progress | In Progress | Done
2020-06-27 | Saturday | Query- forum | Assignment UI and algorithm | Thought of the day | Compiling thought of the day with dashboard | Session UI and Algorithm | Thoughts of day finalized
|  | In-Progress | In-Progress | Completed | Completed | In-Progress | Done
2020-06-28 | Sunday | Query- forum | Assignment UI and algorithm | Email Backend and frontend | Compiling email with dashboard | Session UI and Algorithm | Email Page Finalized, feedback completed
|  | In-Progress | In-Progress | Completed | Completed | Done | Done